## Risks
Example Risks and Issues Register - for keeping track of anything that could impact your project
Number | Type | Area | Details of the risk or issue | Likelihood of the risk/issue happening | Impact | Risk Mitigation - what you could do to reduce of eliminate the risk | Update - actions taken relating to the risk | Status
1 | Risk | Project | Lack of availablity of internal people/resources | Unlikely | High | Ensure resource requirements are known early. Keep across any BAU activities that could impact resource availability | 1/2/2021 - AB - Met with xyz on Tues 28th Jan to continue conversation 6/2/2021 - KH - Was advised of new work coming into team, but secured 50% of TM's time until end of project | Open
2 | Risk | Change & Communication | Key Supplier contact no longer available | Possible | Medium | Build a relationship with more than 1 Supplier contact. Make sure that multiple contacts are across the project and can make decisions | 2/2/2021 - KH - Meeting on 1/2 with 3 Supplier contacts to get them across the project | Open
3 | Risk | Technical | Solution may not be able to deliver the right level of reporting to support the needs | Possible | High | Gather all reports required. Assess what reports are critical. Consider extracting the data and reporting outside the application, if it can't do what's needed. | 3/1/2021 - KH - Review of some of the requirements | Open
4 | Issue | Project | Not able to deliver in time | Possible | Medium | Ensure that timelines are really achievable Agree on Minimum Viable Product for delivery in case timeline starts blowing out |  | Open
5 | Risk | Project | The cost of delivery might be above what is in the budget | Likely | High | Possibly remove some of the scope?
Some examples of risk areas:
Project
Change and People
Technical
Product specific
Transition to Business As Usual (BAU)
Delivered - remain once in BAU

## Lists
Area | Type | Likelihood | Impact | Status
Project | Risk | Unlikely | High | New
Change & Communication | Issue | Possible | Medium | Open
Technical |  | Likely | Low | Closed
…......... |  | Happening